## Sheet1
Grey = Did not finish
Yellow = Progress |  | 2021-05-03 | [6 empty] | 2021-05-10 | [6 empty] | 2021-05-17 | [6 empty] | 2021-05-24 | [6 empty] | 2021-05-31 | [6 empty] | 2021-06-07 | [6 empty] | 2021-06-14 | [6 empty] | 2021-06-21 | [6 empty] | 2021-06-28 |  |  | 2021-07-01 |  |  |  | 2021-07-06 |  |  |  |  | 2021-07-12
Green = Done
Number in collored cell represents time spent on that day in hours |  | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 12 | 13 | 14 | 15
TASK | DAYS | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | M | T | W | F
Read over slides and find topic | bar: 5 W; 7 F
Learning about GATE | bar: 7 F; 9 S to 10 M; 27 T
Read over research articles | bar: 11 T
Title, abstract and proposal (DRAFT) |  | 11 T: 4
Read over Java code in preperation for Thursday meeting | bar: 12 W
Edit and submit proposal | bar: 13 T
Run Java code with correct output and no problems |  | 18 T: 2; 19 W: 3; 20 T: 5; 21 F: 2; 26 W: 3; 27 T: 4
Familiarize with JAPE rules and stability-corpus |  | 22 S: 2
Add JAPE rules in Java code |  | 27 T: 1; 28 F: 2; 29 S: 1; 1 T: 1; 12 S: 2; 13 S: 3; 14 M: 2; 15 T: 4; 16 W: 4; 17 T: 3; 18 F: 1; 19 S: 1; 20 S: 1; 21 M: 4; 23 W: 2; 24 T: 1; 25 F: 10; 27 S: 3; 28 M: 4; 5 M: 9; 6 T: 8; 7 W: 8; 8 T: 6
First Progress Report |  | 30 S: 3; 31 M: 5
Look for spot in Code to add JAPE rules |  | 7 M: 1; 8 T: 4; 9 W: 5; 10 T: 4
Progress report 2 |  | 11 F: 3
Draft |  | 21 M: 7
Presentation |  | 9 F: 5; 12 M: 8; 13 T: 12
Final report |  | 12 M: 2; 13 T: 3; 14 W: 3; 15 F: 12